## TestPlanDetails
SWAGLABS - Test Plan
Test Plan Name | SwagBug-Fucntional test plan |  |  | Project Number | ABC-111 | Total Test cases Planned | 25
Project team | NameA,Name B ,…. |  |  | Business Area | Operations | Test case compeleted | 20
Created By | Saril Priappan | Revised By | Saril Priappan |  |  | Total applicable test cases | 20
Created Date | 45592 | Revised Date | 2024-10-31 |  |  | Pass Percentage | 72%
Tested by | Tester A, Tester B, Tester C | Test complete date | 2024-10-31 |  |  | Fail percentage | 28%
Project Goal | Project description to be entered here |  |  |  |  | % complete | 80%
Reviewers

## User Stories
User Story description | User story # | Test case traceability
User Access
US1: As a standard standard user, I want to log in with valid credentials so that I can access my account and browse available products. | UA-ST1 | TC-UA-001,TC-UA-002,TC-UA-003,TC-UA-004,TC-UA-005,TC-UA-006,TC-UA-007,TC-UA-008,TC-UA-009
US2: As a standard user, I want to see error messages when I enter incorrect credentials so that I can ensure my login is protected | UA-ST2 | TC-UA-002, TC-UA-003
US3: As a standard user, I want my account is logged out when I click on logout option from the menu so that my current session is closed | UA-ST3 | [to be filled]
[add more as per product backlog] |  | [to be filled]
Product List |  | [to be filled]
US1: As a logged in user, I want to view a list of all available products so that I can browse items on the products all page | PL-ST1 | [to be filled]
US2: As a logged in user, I want to see product details - name, price, and image, so I can understand overview of each item. | PL-ST2 | [to be filled]
US3: As a logged in user, I want to be able to sort products by price low to high and vice versa and name alphabetical ascending and descending order so that I can easily find items according to my needs. | PL-ST3 | [to be filled]
[add more as per product backlog] |  | [to be filled]
Product Description |  | [to be filled]
US1: As a standard user, I want to click on a product from the list to view its detailed page, so I can see full description and other larger picture and pricing information | PD-ST1 | [to be filled]
US2: As a standard user, I want an option to add the product to my cart directly from the product details page so that I can purchase it conveniently. | PD-ST2 | [to be filled]
[add more as per product backlog] |  | [to be filled]
Adding to Cart |  | [to be filled]
US1: As a standard user, I want to add products to my cart from both the product catalogue and product details page so that I can easily keep track of items I intend to purchase. | ATC-ST1 | [to be filled]
US2: As a standard user, I want to view all items in my cart with their names, quantities, and prices so that I can review my selections before checkout. | ATC-ST2 | [to be filled]
US3: As a standard user, I want the option to remove items from my cart so that I can adjust my order as needed. | ATC-ST3 | [to be filled]
US4: As a standard user, I want to see the total price of items in my cart, including taxes or discounts, so I know the full amount I will be charged. | ATC-ST4 | [to be filled]
US5: As a standard user, I want to adjust the quantity of each item in my cart so that I can buy the exact amount I need. | ATC-ST5 | [to be filled]
[add more as per product backlog] |  | [to be filled]
Checkout confirmation |  | [to be filled]
US1: As a standard user, I want to start the checkout process from my cart so that I can complete my purchase. | CC-ST1 | [to be filled]
US2: As a standard user, I want to provide my shipping details during checkout so that my items can be delivered to the right address. | CC-ST2 | [to be filled]
US3: As a standard user, I want to select my preferred payment method and enter payment information securely so that I can make a purchase. | CC-ST3 | [to be filled]
US4: As a standard user, I want to receive an order confirmation after completing the checkout so that I know my order was successful. | CC-ST4 | [to be filled]
US5: As a standard user, I want an option to review and edit my order details before final confirmation to avoid mistakes. | CC-ST5 | [to be filled]
[add more as per product backlog] |  | [to be filled]
About module |  | [to be filled]
US1: As a standard user, I want to view the application details and contact information when I click on about option from the menu so that I can contact the merchant if needed. | AM-ST1 | [to be filled]
[add more as per product backlog] |  | [to be filled]
Reset app state module |  | [to be filled]
US1: As a logged in user, I want to reset the app and cart to the initial logged state so that I can start the actions fresh. | RA-ST1 | [to be filled]
[add more as per product backlog] |  | [to be filled]
Performance and security |  | [to be filled]
US1: As a standard user, I want to use the website with out any performance issues so that I can navigate to pages back and forth seamlessly | PS-ST1 | [to be filled]
US2: As a standard user , I want to website to return to login page when I copy paste the logged in user state URL is entered in another browser or window so that others cant access my account without typing the my username and password. | PS-ST2 | [to be filled]
[add more as per product backlog] |  | [to be filled]

## TC-User Access
Test case # | Userstory # | Priortity(1,2,3) | Severity(1,2,3) | Test case title | Test cases description | Pre-requisites | Data input | Expected Results | Actual results | Execution status | Test Cycle | Coverd in Automated Regression test suite | Date of creation/Modification | Date of execution | Tested by | Comments | JIRA defect Ref | Defect closure date
TC-UA-001 | UA-ST1 | 1 | 1 | Verify that a Valid logged-in user can see a list of all available products. | Steps: Log in as a user. Navigate to the products page. Verify that a list of products is displayed. | Test data is created for valid and invalid users user clicks on URL -> https://www.saucedemo.com/v1/index.html | Valid user name : standard_user Valid Password: secret_sauce | User successfully logs in and is navigates to products all page | Successful login.List of products is displayed. | Pass | CY1 | Yes | 2024-10-29 | 2024-10-31 | Tester A
TC-UA-002 | UA-ST2 | 1 | 1 | Verify that a invalid logged-in user cant login | Steps: Log in as a user. Navigate to the products page. Verify that a list of products is displayed. | Test data is created for valid and invalid users user clicks on URL -> https://www.saucedemo.com/v1/index.html | Invalid user name : lockedout_user Valid Password: secret_sauce | System displays an error message "Epic sadface: Username and password do not match any user in this service" | user login failed with expected message | Pass | CY1 | Yes | 2024-10-29 | 2024-10-31 | Tester A
TC-UA-003 | UA-ST2 | 1 | 1 | Verify that a logged-in user can see product details (name, price, and image). | Steps: Log in as a user. Navigate to the products page. Select a product from the list. Verify that the product details (name, price, and image) are displayed. | Test data is created for valid and invalid users user clicks on URL -> https://www.saucedemo.com/v1/index.html | Valid user name : standard_user Valid Password: secret_sauce | The product details (name, price, and image) are displayed on the page. | Successful login.List of products is displayed. | Pass | CY1 | Yes | 2024-10-29 | 2024-10-31 | Tester A
TC-UA-004 | UA-ST1 | 1 | 1 | Valid Login with Minimum Username & Password Length | Steps: Enter a username with minimum length (5 characters). Enter a password with minimum length (8 characters). Click on "Login" button. | User is on login page | Username: ABCDE Password: 12345678 | User successfully logs in and is navigates to products all page | user login failed with expected message | Fail | CY1 | No | 2024-10-29 | 2024-10-31 | Tester A
TC-UA-005 | UA-ST1 | 1 | 1 | Valid Login with Maximum Username & Password Length | Steps: Enter a username with maximum length (15 characters). Enter a password with maximum length (20 characters). Click on "Login" button. | User is on login page | Username: ABCDEFGHIJKLMNO Password: 12345678901234567890 | User successfully logs in and is navigates to products all page | user login failed with expected message | Fail | CY1 | No | 2024-10-29 | 2024-10-31 | Tester A
TC-UA-006 | UA-ST1 | 1 | 1 | Invalid Login with Username Below Minimum Length | Steps: Enter a username with fewer than 5 characters. Enter a valid password. Click on "Login" button. | User is on login page | Username: ABCD Password: 12345678 | Login fails, error message: "Username must be at least 5 characters." | user login failed with expected message | Fail | CY1 | No | 2024-10-29 | 2024-10-31 | Tester A
TC-UA-007 | UA-ST1 | 1 | 1 | Invalid Login with Password Below Minimum Length | Steps: Enter a valid username. Enter a password with fewer than 8 characters. Click on "Login" button. | User is on login page | Username: ABCDE Password: 1234567 | Login fails, error message: "Password must be at least 8 characters." | user login failed with expected message | Fail | CY1 | No | 2024-10-29 | 2024-10-31 | Tester A
TC-UA-008 | UA-ST1 | 1 | 1 | Invalid Login with Special Characters in Username | Steps: Enter a username with special characters. Enter a valid password. Click on "Login" button. | User is on login page | Username: ABCD@ Password: 12345678 | Login fails, error message: "Username can only contain alphabets and _ characters" | user login failed but error message is wrong | Fail | CY1 | No | 2024-10-29 | 2024-10-31 | Tester A
TC-UA-009 | UA-ST1 | 1 | 1 | Invalid Login with Empty Username | Steps: Leave the username field empty. Enter a valid password. Click on "Login" button. | User is on login page | Username: Password: 12345678 | Login fails, error message: "Username is required" | user login failed with expected message | Pass | CY1 | No | 2024-10-29 | 2024-10-31 | Tester A

## TC-Product List
Test case # | Userstory # | Priortity | Severity | Test case title | Test cases description | pre-requisites | Data input | Expected Results | Actual results | Execution status | Test Cycle | Coverd in Automated Regression test suite | Date of creation/Modification | Date of execution | Tested by | Comments | JIRA defect Ref | Defect closure date
TC-PL-001 | PL-ST1 | 1 | 1 | Verify that a logged-in user can see a list of all available products. | Steps: Log in as a user. Navigate to the products page. Verify that a list of products is displayed. | A user account exists. The user is logged in. Products are available in the system |  | A list of products is displayed on the page. | Products displayed on the page | Pass | CY1 | Yes | 2024-10-29 | 2024-10-31 | Tester B
TC-PL-002 | PL-ST2 | 1 | 1 | Verify that a logged-in user can see product details (name, price, and image). | Steps: Log in as a user. Navigate to the products page. Select a product from the list. Verify that the product details (name, price, and image) are displayed. | A user account exists. The user is logged in. Products are available in the system. |  | The product details (name, price, and image) are displayed on the page. | The product details (name, price, and image) are displayed on the page. | Pass | CY1 | Yes | 2024-10-29 | 2024-10-31 | Tester B
TC-PL-003 | PL-ST3 | 2 | 2 | Verify that a logged-in user can sort products by price and name. | Steps: Log in as a user. Navigate to the products page. Click on the "Price" or "Name" sorting options. Verify that the products are sorted correctly. | A user account exists. The user is logged in. Products are available in the system. |  | The products are sorted correctly based on the selected sorting option. | The products are sorted correctly based on the selected sorting option. | Pass | CY1 | Yes | 2024-10-29 | 2024-10-31 | Tester B

## TC-Product Descripton
Test case # | Userstory # | Priortity | Severity | Test case title | Test cases description | pre-requisites | Data input | Expected Results | Actual results | Execution status | Test Cycle | Coverd in Automated Regression test suite | Date of creation/Modification | Date of execution | Tested by | Comments | JIRA defect Ref | Defect closure date
TC-PD-001 | PD-ST1 | 1 | 1 | Verify that a user can view the detailed page of a product. | Steps: Navigate to the products page. Select a product from the list. Verify that the product details page is displayed. | A user account exists. The user is logged in. Products are available in the system. |  | The product details page is displayed with the full description, larger pictures, and pricing information. | Product details page is displayed with the full description, larger pictures, and pricing information. | Pass | CY1 | Yes | 2024-10-29 | 2024-10-31 | Tester C
TC-PD-002 | PD-ST2 | 1 | 1 | Verify that a user can add a product to their cart from the product details page. | Steps: Navigate to the product details page. Click on the "Add to Cart" button. Verify that the product is added to the cart. | A user account exists. The user is logged in. Products are available in the system. |  | The product is added to the cart. | product is added to the cart. | Pass | CY1 | Yes | 2024-10-29 | 2024-10-31 | Tester C

## TC-Adding to Cart
Test case # | Userstory # | Priortity | Severity | Test case title | Test cases description | pre-requisites | Data input | Expected Results | Actual results | Execution status | Test Cycle | Coverd in Automated Regression test suite | Date of creation/Modification | Date of execution | Tested by | Comments | JIRA defect Ref | Defect closure date
TC-ATC-001 | ATC-ST1 | 1 | 1 | Verify that a user can add products to their cart from both the product catalog and product details page. | Steps: Navigate to the products page. Select a product from the list and add it to the cart. Navigate to the product details page for the same product. Add the product to the cart again. Verify that the product is added to the cart twice. | A user account exists. The user is logged in. Products are available in the system. |  | The product is added to the cart twice. | No option to add the item again. Add to car is changed to remove button and not way of incrementing the number of item to be selected | Fail | CY1 | No | 2024-10-29 | 2024-10-31 | Tester A
TC-ATC-002 | ATC-ST2 | 2 | 2 | Verify that a user can add products to their cart from both the product catalog and product details page. | Steps: Navigate to the products page. Select a product from the list and add it to the cart. Navigate to the product details page for the same product. Remove the product from add to cart Check the cart badge and cart details. Navigate to the product details page for the same product. Add the product to the cart again. Verify that the product is added to the cart again | A user account exists. The user is logged in. Products are available in the system. |  | The product is able to add from list and also from product details page. Cart is properly updated the correct information. | The product is added from list and also from product details page. Cart is properly updated the correct information. | Pass | CY1 | No | 2024-10-29 | 2024-10-31 | Tester A

## TC-Checkout confirmation
Test case # | Userstory # | Priortity | Severity | Test case title | Test cases description | pre-requisites | Data input | Expected Results | Actual results | Execution status | Test Cycle | Coverd in Automated Regression test suite | Date of creation/Modification | Date of execution | Tested by | Comments | JIRA defect Ref | Defect closure date
TC-CC-001 | CC-ST1 | 1 | 1 | Verify that a user can start the checkout process from their cart. | Steps: Add products to the cart. Navigate to the cart page. Click on the "Checkout" button. Verify that the checkout page is displayed. | Products are available in the system. Products have been added to the cart. |  | The checkout page is displayed. | Checkout page displayed | Pass | CY1 | Yes | 2024-10-29 | 2024-10-31 | Tester A
TC-CC-002 | CC-ST2 | 1 | 1 | Verify that a user can provide their shipping details during checkout. | Steps: Navigate to the checkout page. Enter the shipping address. Click on the "Continue" button. Verify that the shipping address is appeared In the confirmation page | Products are available in the system. Products have been added to the cart. |  | The shipping address is available in the confirmation page | all details captured is available in the checkout confirmation page | Pass | CY1 | Yes | 2024-10-29 | 2024-10-31 | Tester A
TC-CC-003 | CC-ST3 | 1 | 1 | Verify that a user can Complete the check out process after validating the cart confirmation page | Steps: Navigate to the checkout page. Enter the shipping address. Click on the "Continue" button. Verify that the shipping address is appeared In the confirmation page Click on finish button Order confirmation page is displayed | Products are available in the system. Products have been added to the cart. |  | Thank you for your order message. User successfully complete the order. | Check out complete and thank you for order message appeared | Pass | CY1 | Yes | 2024-10-29 | 2024-10-31 | Tester A

## TC-Performace and security
Test case # | Userstory # | Priortity | Severity | Test case title | Test cases description | pre-requisites | Data input | Expected Results | Actual results | Execution status | Test Cycle | Coverd in Automated Regression test suite | Date of creation/Modification | Date of execution | Tested by | Comments | JIRA defect Ref | Defect closure date
TC-PS-001 | PS-ST1 | 1 | 1 | Verify that the website loads quickly and pages transition smoothly without any performance issues. | Steps: Launch the website. Navigate to different pages within the website. Verify that the pages load quickly and without any delays. Click the back and forward buttons in the browser to navigate between pages. Verify that the pages load quickly and without any delays. | The website is accessible. The user's internet connection is stable. | Valid user name : performance_glitch_user Valid Password: secret_sauce | The website loads quickly. Pages transition smoothly without any delays. The back and forward buttons function correctly. | Website does not load quickly. It takes around 10 seconds to navigates to each pages when login button is clicked | Fail | CY1 | Yes | 2024-10-29 | 2024-10-31 | Tester A | NFT
TC-PS-002 | PS-ST2 | 1 | 1 | Verify that the website redirects to the login page when a logged-in user state URL is copied and pasted into another browser or window. | Steps: Log in to the website as a standard user. Copy the current URL of the website. Open a new browser or window. Paste the copied URL into the address bar and navigate to the website. Verify that the website redirects to the login page. | The website has a login functionality. The user is logged in to the website. | Valid user name : standard_user Valid Password: secret_sauce | The website redirects to the login page when the logged-in user state URL is accessed from a different browser or window. | anyone can access with the logged in state URL in all the browsers. Security is compromised | Fail | CY1 | No | 2024-10-29 | 2024-10-31 | Tester A | NFT

## TC-About module
Test case # | Userstory # | Priortity | Severity | Test case title | Test cases description | pre-requisites | Data input | Expected Results | Actual results | Execution status | Test Cycle | Date of creation/Modification | Date of execution | Tested by | Comments | JIRA defect Ref | Defect closure date
Need to design

## TC-Reset app state module
Test case # | Userstory # | Priortity | Severity | Test case title | Test cases description | pre-requisites | Data input | Expected Results | Actual results | Execution status | Test Cycle | Date of creation/Modification | Date of execution | Tested by | Comments | JIRA defect Ref | Defect closure date
need to design